## Home
DRAFT ¦ PRE-DECISIONAL ¦ NOT FOR DISTRIBUTION
Tribal Broadband Planning Toolkit Tribal Broadband Plan Template
Welcome to the Tribal Broadband Plan template of the Tribal Broadband Planning Toolkit! This Toolkit provides tribal entities with the guidance, knowledge, and resources to design, implement, and maintain a broadband plan in their communities. Made up of seven worksheets, this Toolkit offers insights, interactive tools, and links to technical assistance resources for every stage of the broadband planning journey. While the worksheets provide space for interactive activities, you can take those activities even further in the spreadsheets here to expound on the specifics of your broadband plan. While we understand that there is no one-size-fits-all approach to crafting a broadband plan, we are hopeful this Toolkit provides foundational resources to get you started. Note: This template is meant to be used as a complement to the BroadbandUSA Tribal Broadband Planning Toolkit worksheets, which can be accessed here [insert link].
ASSEMBLE A TEAM
HOME
SELECT THE RIGHT SOLUTIONS
BUILD RELATIONSHIPS FOR SUCCESS
EXPLORE THE DATA
DETERMINE YOUR PRIORITIES
CHART A PATH FORWARD
PREPARE A BUDGET

## Assemble a Team
DRAFT ¦ PRE-DECISIONAL ¦ NOT FOR DISTRIBUTION
Assemble a Team Build a team with the skills needed to accomplish your broadband goals.
Team Role | Responsibilities | Team Member | Organization Affiliation | Position at Organization | Email Address | Phone Number
Internal project champion | Sponsors and drives planning activities forward
Project manager | Sets meeting agenda and organizes team dynamics
Administrative assistant | Organizes team documentation and resources
Financial manager | Manages team budget and funding as applicable
Technical and policy expert(s) | Provides subject matter expertise on broadband-related matters
Data expert | Provides data collection, management, and control expertise
Outreach coordinator | Leads outreach to tribal community members
Liaison to federal, state, and local partners | Leads outreach to federal, state, and local partners
ASSEMBLE A TEAM
HOME
SELECT THE RIGHT SOLUTIONS
BUILD RELATIONSHIPS FOR SUCCESS
EXPLORE THE DATA
DETERMINE YOUR PRIORITIES
CHART A PATH FORWARD
PREPARE A BUDGET

## Determine Your Priorities
DRAFT ¦ PRE-DECISIONAL ¦ NOT FOR DISTRIBUTION
Determine Your Priorities Create a set of priorities to help your community build or expand meaningful access to broadband.
| Conversation Date | Team Member Facilitating the Conversation | Conversation Audience (Name of Person or Group) | Conversation Forum (e.g., Email, Zoom, Phone) | Question | Answers
Example: | 2022-02-05 | Last Name, First Name | Tribal library | In-Person | How is broadband used by customers at the library? | We have a computer cluster with outdated computers and slow internet. Weekdays are very popular for internet use, where there is often a line of people waiting to use our computers to check their e-mails.
ASSEMBLE A TEAM
HOME
SELECT THE RIGHT SOLUTIONS
BUILD RELATIONSHIPS FOR SUCCESS
EXPLORE THE DATA
DETERMINE YOUR PRIORITIES
CHART A PATH FORWARD
PREPARE A BUDGET

## Explore the Data
DRAFT ¦ PRE-DECISIONAL ¦ NOT FOR DISTRIBUTION
Explore the Data Measure current broadband availability and use in your community.
Topic | Data Source | Source Description | Key Questions | Community Context (Input answer for your community)
Service Provided | IBN | Displays areas where no provider reports offering service at 25/3 Mbps | Does an ISP provide service in your community at a standard of 25/3 Mbps?
| FCC | Displays number of fixed broadband providers in an area Lists providers that offer services for a specific location, based on address | Are there ISPs that serve your community? If so, what are they and where do they serve?
Internet Access | IBN | Displays areas where 25% or more of households report no Internet access | Is your community in an area where 25% or more of households report no internet access?
| ACS | Displays how many households report an internet subscription Of households that reporting an Internet subscription, displays what type | How many households in your community have an internet subscription? What is the most common type of broadband technology used in your community?
| NTIA Data Explorer | Of households that use internet, displays proportion of households with each type of Internet service | Of households that have internet service, what proportion use each type of internet service?
Speed | IBN | Displays areas that have speeds below 25/3 | Does your community experience internet speeds below 25/3 Mbps?
| FCC | Displays how many providers provide service at various speeds in an area | Are there ISPs that serve your community? If so, what level of service do they provide
| Speedtest & M-Lab | Allows you to conduct your own speed test | What are different internet speeds that users in your community experience?
Devices | IBN | Displays areas where 25% or more of households report no computer, smartphone, or tablet | Is your community in an area where 25% or more of households report no computer, smartphone, or tablet?
| ACS | Displays how many households report having a computer Of households that report having a computer device, displays what type | How many households in your community have a computer? Of those, how many households have which type (e.g., tablet, laptop)?
| NTIA Data Explorer | Displays percentage of individuals that use different types of digital devices | What types of devices do individuals in your community use to access the internet (e.g., smartphone, tablet)? What proportion of the community use each type of device?
Activity & Location of Use | NTIA Data Explorer | Displays percentage of individuals who use the internet to do various activities Displays percentage of individuals who use the internet at various locations | What activities do individuals in your community use the internet for (e.g., searching for a job, using email)? What proportion of the community uses the internet for each of these activities? What locations to individuals in your community use the internet at (e.g., cafe, home, work)? What proportion of the community uses the internet at each of these locations?
ASSEMBLE A TEAM
HOME
SELECT THE RIGHT SOLUTIONS
BUILD RELATIONSHIPS FOR SUCCESS
EXPLORE THE DATA
DETERMINE YOUR PRIORITIES
CHART A PATH FORWARD
PREPARE A BUDGET

## Build Relationships for Success
DRAFT ¦ PRE-DECISIONAL ¦ NOT FOR DISTRIBUTION
Build Relationships for Success Identify partners to engage throughout the broadband planning process.
| Category Select from the dropdown menu | Name | Organization Affiliation | Position at Organization | Email Address | Phone Number | Engagement Purpose Select from the dropdown menu | Date of Last Engagement | Notes
Example: | Business | Last Name, First Name | State of X Broadband Office | Program Specialist | lastname.firstname@state.broadband.gov | 123-456-7890 | Inform | 2021-12-05 | First Name encouraged us to look into State X's Broadband Grant Program as a potential funding source for our infrastructure program
ASSEMBLE A TEAM
HOME
SELECT THE RIGHT SOLUTIONS
BUILD RELATIONSHIPS FOR SUCCESS
EXPLORE THE DATA
DETERMINE YOUR PRIORITIES
CHART A PATH FORWARD
PREPARE A BUDGET

## Select the Right Solutions
DRAFT ¦ PRE-DECISIONAL ¦ NOT FOR DISTRIBUTION
Select the Right Solutions Determine the specific methods to use to reach your broadband goals.
| Program Name | Department | Agency/Bureau | Important Program Dates | Funding Amount | Program Point of Contact | Relevant Notes
Example: | State Broadband Grant Program | State Department of Commerce | State of X | Application Deadline: 12/2/22 | Up to $500K | Last Name, First Name
ASSEMBLE A TEAM
HOME
BUILD RELATIONSHIPS FOR SUCCESS
EXPLORE THE DATA
DETERMINE YOUR PRIORITIES
CHART A PATH FORWARD
SELECT THE RIGHT SOLUTIONS
PREPARE A BUDGET

## Prepare a Budget
DRAFT ¦ PRE-DECISIONAL ¦ NOT FOR DISTRIBUTION
INSTRUCTIONS for PREPARE A BUDGET: • For infrastructure projects, complete the budget template on the left (starting at B5). This template includes sections for the three phases of an infrastructure project - Pre-Construction, Construction, and Network Sustainability and Operations. • For use & adoption / digital inclusion & equity projects, complete the budget template on the right (starting at J5), which includes just one phase of work. • Complete the budget template by filling in every row with details for the project. The template includes one row per Category + Sub-Category pair, so insert new rows as needed. For example, if the project requires two pieces of Equipment for Site Work during Phase 2 Construction, insert a new row after the original one to include the second piece of Equipment. • For all instances of Personnel, input the Quantity in terms of hours, and input the Unit Cost as hourly pay. Include in the Narrative the percentage of that person's time that willl be dedicated to the Category + Sub-Category. • For all instances of Fringe Benefits, input the Quantity as the rate of pay, and input the Unit Cost as the personnel's annual pay. Also state the rate in the Narrative. For example, if fringe benefits are set at 20% and someone is paid $80 / hour, insert 0.2 as the Quantity and $166,400 ($80 *2,080) as the Unit Cost for an Amount Requested of $33,280.
Prepare a Budget Set a budget for the various expenses included in your broadband plan.
| INFRASTRUCTURE PROJECT BUDGET | [6 empty] | USE & ADOPTION (DIGITAL INCLUSION & EQUITY) PROJECT BUDGET
| Category + Sub-Category | Item | Quantity | Unit Cost | Amount Requested | Narrative | Justification | Category + Sub-Category | Item | Quantity | Unit Cost | Amount Requested | Narrative | Justification
Phase 1 | PRE-CONSTRUCTION | [6 empty] | DIGITAL LITERACY
| LAND, STRUCTURES, LEASING | [6 empty] | Personnel |  |  |  | 0
| Personnel |  |  |  | 0 |  |  | Fringe Benefits |  |  |  | 0
| Fringe Benefits |  |  |  | 0 |  |  | Travel |  |  |  | 0
| Travel |  |  |  | 0 |  |  | Equipment |  |  |  | 0
| Equipment |  |  |  | 0 |  |  | Supplies |  |  |  | 0
| Supplies |  |  |  | 0 |  |  | Contractual |  |  |  | 0
| Contractual |  |  |  | 0 |  |  | Other |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0 |  |  | Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0 |  |  | TOTAL
| TOTAL | [6 empty] | WORKFORCE DEVELOPMENT AND TRAINING
| APPRAISALS | [6 empty] | Personnel |  |  |  | 0
| Personnel |  |  |  | 0 |  |  | Fringe Benefits |  |  |  | 0
| Fringe Benefits |  |  |  | 0 |  |  | Travel |  |  |  | 0
| Travel |  |  |  | 0 |  |  | Equipment |  |  |  | 0
| Equipment |  |  |  | 0 |  |  | Supplies |  |  |  | 0
| Supplies |  |  |  | 0 |  |  | Contractual |  |  |  | 0
| Contractual |  |  |  | 0 |  |  | Other |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0 |  |  | Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0 |  |  | TOTAL
| TOTAL | [6 empty] | SUBSIDY OF SERVICE
| RIGHTS-OF-WAY | [6 empty] | Personnel |  |  |  | 0
| Personnel |  |  |  | 0 |  |  | Fringe Benefits |  |  |  | 0
| Fringe Benefits |  |  |  | 0 |  |  | Travel |  |  |  | 0
| Travel |  |  |  | 0 |  |  | Equipment |  |  |  | 0
| Equipment |  |  |  | 0 |  |  | Supplies |  |  |  | 0
| Supplies |  |  |  | 0 |  |  | Contractual |  |  |  | 0
| Contractual |  |  |  | 0 |  |  | Other |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0 |  |  | Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0 |  |  | TOTAL
| TOTAL | [6 empty] | TELEHEALTH
| PERMITTING | [6 empty] | Personnel |  |  |  | 0
| Personnel |  |  |  | 0 |  |  | Fringe Benefits |  |  |  | 0
| Fringe Benefits |  |  |  | 0 |  |  | Travel |  |  |  | 0
| Travel |  |  |  | 0 |  |  | Equipment |  |  |  | 0
| Equipment |  |  |  | 0 |  |  | Supplies |  |  |  | 0
| Supplies |  |  |  | 0 |  |  | Contractual |  |  |  | 0
| Contractual |  |  |  | 0 |  |  | Other |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0 |  |  | Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0 |  |  | TOTAL
| TOTAL | [6 empty] | TELEWORK
| RELOCATION EXPENSES AND PAYMENTS | [6 empty] | Personnel |  |  |  | 0
| Personnel |  |  |  | 0 |  |  | Fringe Benefits |  |  |  | 0
| Fringe Benefits |  |  |  | 0 |  |  | Travel |  |  |  | 0
| Travel |  |  |  | 0 |  |  | Equipment |  |  |  | 0
| Equipment |  |  |  | 0 |  |  | Supplies |  |  |  | 0
| Supplies |  |  |  | 0 |  |  | Contractual |  |  |  | 0
| Contractual |  |  |  | 0 |  |  | Other |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0 |  |  | Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0 |  |  | TOTAL
| TOTAL | [6 empty] | TELE-EDUCATION
| ARCHITECTURAL AND ENGINEERING FEES | [6 empty] | Personnel |  |  |  | 0
| Personnel |  |  |  | 0 |  |  | Fringe Benefits |  |  |  | 0
| Fringe Benefits |  |  |  | 0 |  |  | Travel |  |  |  | 0
| Travel |  |  |  | 0 |  |  | Equipment |  |  |  | 0
| Equipment |  |  |  | 0 |  |  | Supplies |  |  |  | 0
| Supplies |  |  |  | 0 |  |  | Contractual |  |  |  | 0
| Contractual |  |  |  | 0 |  |  | Other |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0 |  |  | Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0 |  |  | TOTAL
TOTAL
ENVIRONMENTAL FEES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
PROJECT INSPECTION FEES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
FEASIBILITY STUDIES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
MISCELLANEOUS
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
Phase 2 | CONSTRUCTION
SITE WORK
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
DEMOLITION AND REMOVAL
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
CONSTRUCTION
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
EQUIPMENT (RENTAL)
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
MOBILIZATION AND DEMOBILIZATION
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
STORAGE
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
MAPPING
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
MISCELLANEOUS
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
Phase 3 | NETWORK SUSTAINABILITY AND OPERATIONS
ADVERTISING AND PROMOTION
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
BAD DEBT EXPENSES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
BANK SERVICE CHARGES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
COMPUTER SOFTWARE
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
DUES AND SUBSCRIPTIONS
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
EQUIPMENT MAINTENANCE
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
LIABILITY INSURANCE
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
LICENSES AND PERMITS
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
MEMBERSHIP FEES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
OFFICE EXPENSES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
OPERATIONS EXPENSES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
COSTS OF GOODS SOLD
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
PERSONNEL EXPENSES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
POSTAGE
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
PROFESSIONAL SERVICES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
RENT EXPENSES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
TRAVEL AND VEHICLES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
UTILITIES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
MAPPING
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
PAYROLL
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
RECONCILIATION DISCREPANCIES
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
WRITE OFF
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
MISCELLANEOUS
| Personnel |  |  |  | 0
| Fringe Benefits |  |  |  | 0
| Travel |  |  |  | 0
| Equipment |  |  |  | 0
| Supplies |  |  |  | 0
| Contractual |  |  |  | 0
| Administrative and Indirect Costs |  |  |  | 0
| Other |  |  |  | 0
TOTAL
ASSEMBLE A TEAM
HOME
BUILD RELATIONSHIPS FOR SUCCESS
EXPLORE THE DATA
DETERMINE YOUR PRIORITIES
CHART A PATH FORWARD
SELECT THE RIGHT SOLUTIONS
PREPARE A BUDGET

## Chart a Path Forward
DRAFT ¦ PRE-DECISIONAL ¦ NOT FOR DISTRIBUTION
Chart a Path Forward Develop a project plan to guide execution of your broadband plan.
| Program Objective | Key Activity | Activity Owner Member of broadband team | Start Date | End Date | Activity Status | Risks | Notes
Example: | 1.1 Provide universal broadband access among school-age children living on tribal lands | Engage all schools during a kick-off meeting within the Reservation to support distribution program | Last Name, First Name | 2021-03-05 | 2021-03-05 | Complete | N/A
Example: | 1.1 Provide universal broadband access among school-age children living on tribal lands | Procure devices for schools | Last Name, First Name | 2021-03-15 | 2021-04-02 | Complete | N/A
ASSEMBLE A TEAM
HOME
BUILD RELATIONSHIPS FOR SUCCESS
EXPLORE THE DATA
DETERMINE YOUR PRIORITIES
CHART A PATH FORWARD
SELECT THE RIGHT SOLUTIONS
PREPARE A BUDGET
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include measurable objective / milestones
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include measurable objective / milestones

## Lists (hidden)
Project Type
Infrastructure
Use & Adoption (Digital Inclusion & Equity)
Infrastructure Project Phases | Use & Adoption Project Phases
PRE-CONSTRUCTION | N/A
CONSTRUCTION
NETWORK SUSTAINABILITY & OPERATIONS
Pre-Construction Categories | Construction Categories | Network Sustainability & Operations Categories
LAND, STRUCTURES, LEASING | SITE WORK | ADVERTISING AND PROMOTION | PERSONNEL EXPENSES
APPRAISALS | DEMOLITION AND REMOVAL | BAD DEBT EXPENSES | POSTAGE
RIGHTS-OF-WAY | CONSTRUCTION | BANK SERVICE CHARGES | PROFESSIONAL SERVICES
PERMITTING | EQUIPMENT (RENTAL) | COMPUTER SOFTWARE | RENT EXPENSES
RELOCATION EXPENSES AND PAYMENTS | MOBILIZATION AND DEMOBILIZATION | DUES AND SUBSCRIPTIONS | TRAVEL AND VEHICLES
ARCHITECTURAL AND ENGINEERING FEES | STORAGE | EQUIPMENT MAINTENANCE | UTILITIES
ENVIRONMENTAL FEES | MAPPING | LIABILITY INSURANCE | PAYROLL
PROJECT INSPECTION FEES | MISCELLANEOUS | LICENSES AND PERMITS | MAPPING
FEASIBILITY STUDIES |  | MEMBERSHIP FEES | RECONCILIATION DISCREPANCIES
MISCELLANEOUS |  | OFFICE EXPENSES | WRITE OFF
|  | OPERATIONS EXPENSES | MISCELLANEOUS
COST OF GOODS SOLD
Use & Adoption Categories
DIGITAL LITERACY
WORKFORCE DEVELOPMENT AND TRAINING
SUBSIDY OF SERVICE
TELEHEALTH
TELEWORK
TELE-EDUCATION
Sub-Categories
Personnel
Fringe Benefits
Travel
Equipment & Devices
Supplies
Contractual
Administrative and Indirect Costs
Other